## Sheet1
Screen | Task | Status (Previous) | Discussed Changes | Status (Current)
File Directory |  | Pending | Pending | Pending
File Upload | 1. Upload File | Completed | Pending (Cosmetic Changes) | Completed
| 2.To Select File Directory | Pending | Pending | Pending
| 3. REIMS API Integration | Completed | Completed | Completed
| 4. Modal To show Digitize File | Completed | Pending (Cosmetic Changes) | Completed
| 5.Filtering Excel Files to Digitization | Completed | Pending (Cosmetic Changes) and Filteration | Completed
| 6. Mutiple Files Restrict 5 and Can able to select Multiple Times | Completed | Completed | Completed
Upload History | 1. Files To View in Table | Completed | Completed | Completed
| 2. Search Functionality | Completed | Completed | Completed
| 3. Action Buttons (Digitize) | Pending | Pending | Pending
| 4. Fetch API Integration Data | Completed | Completed | Completed
Template Directory | 1. Created Table To Filter Templates | Completed | Pending (Cosmetic Changes) | Completed
| 2. Added Modal New Templates | Completed | Pending (Cosmetic Changes) Drawer, Template form with sheet and new row | Pending
| 3. Edit Template Modal | Pending | Pending | Pending
| 4. View Existing Templates | Completed | Pending (Cosmetic Changes) | Completed
Digitize File | 1. Upload File To Sceen Completed | Completed | Pending | Pending
| 2. Table To Select Template | Completed | Pending | Pending
| 3. Upload Files To ADLS | Blocked/ API Dependency | Blocked/ API Dependency | Blocked/ API Dependency
| 4. Fetch API Integration Templates | Completed | Pending | Pending
| 5. Ditize File Screen to Upload File Screen Work Flow | In Progress | In Progress | In Progress
Digitize History | 1. Files To View in Table | Completed | Completed | Completed
| 2. Search Functionality | Completed | Completed | Completed
| 3. Fetch API Integration | Completed | Completed | Completed